## FB Vs TM
📊 Project Management Documents for Fixed Bid vs T&M Decision | [5 empty] | ✅ Legend:
# | Document / Matrix Name | Project Management Purpose | Usage in Fixed Bid | Usage in T&M | Notes | ✅ – Applicable
1 | Business Case | Justifies project investment and engagement model | ✅✅✅ | ✅✅ | Helps in selecting cost-effective and risk-balanced model | ✅✅ – Strongly Recommended
2 | Scope of Work (SOW) | Clearly defines project deliverables, scope, timelines | ✅✅✅✅✅ | ✅✅ | Must be highly detailed in Fixed Bid | ✅✅✅ – Essential
3 | Requirements Specification | Documents functional and non-functional requirements | ✅✅✅✅✅ | ✅✅✅ | Completeness of requirements critical for Fixed Bid | ✅✅✅✅ – Critical
4 | Effort Estimation (ROM / Bottom-Up) | Provides initial and refined cost/time estimation | ✅✅✅✅✅ | ✅✅✅✅ | ROM is suitable for T&M; detailed estimation for Fixed | ✅✅✅✅✅ – Mandatory
5 | Cost Benefit Analysis (CBA) | Compares project value with estimated costs under both models | ✅✅✅✅ | ✅✅✅ | A decision-making tool for stakeholders
6 | Risk Register | Identifies and categorizes engagement-specific risks | ✅✅✅✅ | ✅✅✅ | Fixed Bid typically carries higher delivery risk
7 | Pricing Comparison Matrix | Compares costs, flexibility, risk-sharing, and governance under both models | ✅✅✅✅ | ✅✅✅ | A key input to executive decision-makers
8 | Change Management Plan | Defines how changes to scope/cost/timeline will be handled | ✅✅✅✅✅ | ✅✅ | Vital for Fixed Bid to handle scope creep
9 | Project Charter | Formally authorizes the project and defines high-level parameters | ✅✅✅✅ | ✅✅✅ | Helps in stakeholder alignment
10 | Work Breakdown Structure (WBS) | Breaks down deliverables into manageable work packages | ✅✅✅✅ | ✅✅✅✅ | Used for task-level effort tracking
11 | Resource Plan | Details roles, responsibilities, and resource loading | ✅✅✅ | ✅✅✅✅✅ | Especially critical for T&M, where billing is effort-based
12 | Cost Baseline / Budget Plan | Approved estimate of project cost; used for tracking budget performance | ✅✅✅✅✅ | ✅✅ | Needed more strictly in Fixed Bid
13 | Governance Framework | Outlines oversight, reporting, escalation paths | ✅✅✅ | ✅✅✅✅ | Ensures accountability and control
14 | RACI Matrix | Clarifies stakeholder responsibilities across project phases | ✅✅✅✅ | ✅✅✅✅ | Supports ownership clarity regardless of engagement model
15 | Assumptions and Constraints Log | Lists key assumptions that may impact effort, scope, or pricing | ✅✅✅✅ | ✅✅✅ | Forms basis for scope protection in Fixed Bid
16 | Decision Matrix (Model Selection) | Documents evaluation of Fixed Bid vs T&M models using scoring and ranking | ✅✅✅✅ | ✅✅✅ | Useful during procurement or pre-sales phases
17 | Procurement Management Plan | Defines how goods/services will be acquired and contract type rationale | ✅✅✅✅ | ✅✅✅ | Aligned with contractual terms
18 | Communication Plan | Defines stakeholder communication structure, cadence, and methods | ✅✅✅ | ✅✅✅ | Impacts how model-specific reporting happens
19 | KPI & SLA Definition Document | Defines success metrics, performance targets | ✅✅✅✅ | ✅✅✅ | In Fixed Bid, SLAs may be tied to payment milestones
20 | Contract Agreement (Legal) | Defines legal terms, penalties, payment structures | ✅✅✅✅✅ | ✅✅✅✅✅ | Varies significantly between models – detailed for both

## Docs_list
Document/Terminology | Definition | Purpose | Key Components | Role in Fixed-Price Bid | Role in T&M Bid
Request for Proposal (RFP) | A client-issued document outlining project objectives, scope, and requirements to solicit vendor bids. | To communicate project needs and expectations, enabling vendors to propose a suitable contract type. | - Project objectives - Scope overview - Budget constraints - Timeline expectations - Vendor evaluation criteria | Requires detailed scope, deliverables, and timeline to enable accurate fixed-cost estimation. Ensures vendors understand the fixed budget and deliverables. | Outlines high-level goals with flexibility for evolving requirements, signaling T&M as suitable for iterative or unclear projects.
Statement of Work (SOW) | A detailed document specifying the project’s scope, deliverables, tasks, timelines, and acceptance criteria. | To define what the vendor must deliver and how success is measured, forming the basis of the contract. | - Detailed scope and tasks - Milestones or sprint cycles - Acceptance criteria - Payment terms - Roles and responsibilities | Must be highly detailed with clear deliverables, milestones, and fixed costs to minimize ambiguity and vendor risk. | More flexible, focusing on high-level goals and iterative phases, allowing scope adjustments during execution.
Business Requirements Document (BRD) / Functional Requirements Specification (FRS) | A document detailing the functional and non-functional requirements of the project. | To clarify client needs and technical specifications, enabling effort and cost estimation. | - Functional requirements (e.g., features, UI) - Non-functional requirements (e.g., performance, security) - Constraints (e.g., tech stack) - Assumptions and exclusions | Comprehensive and stable requirements are critical for accurate cost estimation and commitment to a fixed price. | Allows for incomplete or evolving requirements, supporting T&M’s flexibility for iterative development.
Work Breakdown Structure (WBS) | A hierarchical breakdown of the project into tasks, subtasks, and deliverables. | To decompose the project into manageable components for estimating time, effort, and resources. | - Task list with descriptions - Estimated effort (hours/resources) - Dependencies and sequence - Deliverables per task | Detailed task estimates ensure the vendor can quote a fixed price with confidence, reducing cost overrun risks. | High-level tasks with estimated ranges allow flexibility in effort, aligning with T&M’s adaptable billing structure.
Risk Assessment Document | A document identifying potential risks, their likelihood, impact, and mitigation strategies. | To evaluate uncertainties that could affect cost, timeline, or scope, guiding contract choice. | - Risk identification (e.g., scope creep, technical issues) - Probability and impact analysis - Mitigation strategies - Contingency plans | Identifies risks to include cost buffers in the fixed price, ensuring vendor profitability despite uncertainties. | Focuses on client-side risks (e.g., cost overruns), as T&M allows billing for actual effort to address risks.
Cost Estimate / Proposal | A vendor-provided document detailing estimated costs, resources, and approach for the project. | To outline financial and resource commitments, helping clients choose between Fixed and T&M. | - Cost breakdown (labor, materials, overhead) - Assumptions and exclusions - Payment schedule - Rate structure (for T&M) | Specifies a total fixed cost based on defined scope, with clear assumptions to avoid disputes. | Provides hourly/daily rates and estimated effort ranges, offering flexibility in total cost based on actual work.
Project Schedule / Timeline | A document outlining the project’s timeline, milestones, and key delivery dates. | To provide a roadmap for execution and assess feasibility within budget and time constraints. | - Milestones or sprint cycles - Task durations - Critical path dependencies - Delivery dates | Rigid milestones and deadlines align with the fixed budget, ensuring timely delivery within scope. | Flexible, iterative phases (e.g., sprints) support ongoing adjustments, accommodating T&M’s adaptability.
Change Management Plan | A document outlining the process for handling scope changes, including approval and cost implications. | To ensure clarity on managing changes, preventing disputes and controlling scope creep. | - Change request process - Approval process - Impact assessment (cost, time) - Revised estimates | Strict process to control scope creep, requiring formal change requests to adjust cost or timeline. | Flexible process, allowing scope changes to be incorporated into ongoing work, billed at agreed rates.

## Questionnaire
Category | Question | Purpose | Fixed-Price Context | T&M Context
Scope | What are the specific deliverables expected? | To define the project’s scope and outputs. | “List all required features for the website (e.g., contact form, blog).” | “Which features are must-haves vs. nice-to-haves for iterative prioritization?”
| Are there any anticipated changes to requirements? | To assess scope stability for contract type. | “Will the scope remain fixed, or are changes expected?” | “How frequently will requirements be reviewed or adjusted?”
Technical | What is the preferred technology stack? | To estimate effort based on technical requirements. | “Must the app use React Native with specific APIs?” | “Are there flexible tech options for iterative development?”
| Are there existing systems to integrate with? | To identify integration complexities. | “Provide API documentation for integration.” | “Can integration be phased across sprints?”
Timeline | What is the desired project completion date? | To align estimates with customer deadlines. | “Is the June 30, 2026, deadline fixed?” | “Are there flexible milestones for iterative delivery?”
Budget | What is the budget range for the project? | To align estimates with financial constraints. | “Is the budget capped at $30,000?” | “Are you comfortable with variable costs based on hours?”
Stakeholders | Who will approve deliverables and provide feedback? | To clarify decision-making processes. | “Who signs off on final deliverables?” | “Who will participate in sprint reviews?”
Risks | Are there known risks or constraints (e.g., regulatory)? | To incorporate risks into estimates. | “Are there compliance requirements impacting cost?” | “Can risks be addressed iteratively?”

## RFI_RFP_Estimation
Process/Step | Definition | Purpose | Key Components | Fixed-Price Application | T&M Application | Example
RFI Analysis | Reviewing the RFI to understand customer needs, scope, and constraints. | To assess project feasibility and determine if Fixed or T&M is suitable. | - Goals and objectives - High-level scope - Budget/timeline constraints - Vendor capabilities | Identifies if scope is clear enough for a Fixed-Price estimate (e.g., specific deliverables like a website). | Highlights vague or evolving needs, favoring T&M (e.g., exploratory software development). | RFI Example: “Develop a mobile app for e-commerce.” Fixed: Needs specific features defined. T&M: Allows iterative feature development.
High-Level Effort Estimation (RFI) | Estimating broad effort and cost ranges based on RFI data. | To provide a ballpark estimate for initial discussions. | - Effort ranges (hours) - Resource types - Cost ranges - Risk assumptions | Offers a cost range (e.g., $50,000–$70,000) based on assumed scope to gauge Fixed-Price feasibility. | Suggests hourly rates (e.g., $100/hour) and estimated hours (e.g., 500–700) for T&M flexibility. | Example: For a website, Fixed: $30,000–$40,000. T&M: 300–400 hours at $100/hour.
Risk Assessment (RFI) | Identifying high-level risks impacting cost or timeline. | To evaluate uncertainties that influence contract type. | - Risk list (e.g., unclear scope) - Probability and impact - Mitigation strategies | Highlights risks requiring cost buffers for Fixed-Price (e.g., 15% contingency for API issues). | Identifies risks that increase hours, supporting T&M’s flexibility. | Example: Risk of unclear APIs. Fixed: Add $5,000 buffer. T&M: Bill additional hours as needed.
RFP Scope Analysis | Reviewing RFP for detailed requirements, deliverables, and constraints. | To understand the project scope for accurate estimation. | - Deliverables - Acceptance criteria - Timeline - Technical specs | Ensures scope is well-defined to support a Fixed-Price bid (e.g., 5-page website with specific features). | Accommodates vague or iterative scope, favoring T&M (e.g., agile software development). | RFP Example: “Build a CRM system.” Fixed: Needs detailed features. T&M: Allows phased development.
Work Breakdown Structure (WBS) | Breaking the project into tasks and subtasks for effort estimation. | To estimate time, resources, and costs for each project component. | - Task list - Effort estimates (hours) - Dependencies - Deliverables | Detailed WBS ensures accurate Fixed-Price estimate (e.g., 200 hours for development). | High-level WBS with ranges supports T&M’s flexibility (e.g., 50–70 hours per sprint). | Example: Website project. Fixed: “Design: 50 hours, Development: 100 hours.” T&M: “Sprint 1: 40–60 hours.”
Cost Estimation (RFP) | Calculating costs based on effort, resources, and risks. | To propose a competitive bid aligned with customer expectations. | - Labor costs (hours × rates) - Material costs - Contingency buffers - Rate structure (T&M) | Fixed cost based on total effort + buffer (e.g., $20,000 with 10% contingency). | Hourly rates with estimated hours (e.g., $100/hour for 200–300 hours). | Example: Fixed: $25,000 for app development. T&M: $120/hour for 250–350 hours.
Timeline Estimation | Mapping tasks to a project schedule. | To ensure the project meets customer deadlines. | - Milestones/sprints - Task durations - Critical path | Rigid milestones for Fixed-Price (e.g., launch by Week 12). | Flexible sprints for T&M (e.g., monthly deliverables). | Example: Fixed: “Design by Week 4, Launch by Week 12.” T&M: “Sprint 1 by Month 1.”
Questionnaire Development | Creating questions to clarify RFI/RFP ambiguities. | To refine scope, reduce risks, and improve estimation accuracy. | - Scope questions - Technical questions - Timeline/budget questions - Stakeholder roles | Locks in scope details for Fixed-Price (e.g., “What are the exact features required?”). | Seeks flexibility for T&M (e.g., “How often will requirements be reviewed?”). | Example: Fixed: “List all required website pages.” T&M: “Will features be prioritized per sprint?”
Customer Response Integration | Updating estimates based on questionnaire answers. | To finalize the bid with accurate scope, cost, and timeline. | - Revised WBS - Updated cost estimate - Adjusted risk assessment | Refines Fixed-Price bid to ensure cost certainty (e.g., $22,000 after clarifying scope). | Adjusts T&M estimates for hours/rates (e.g., 300 hours after confirming iterative needs). | Example: Fixed: Adjust cost after confirming 5 pages. T&M: Update hours after clarifying sprint cadence.

## RACI
Project Task | Delivery Manager | Project Manager | Tech Lead | QA Lead | Client PM | PMO |  | Activity/Area | Responsible (R) | Accountable (A) | Consulted (C) | Informed (I)
Project Kickoff Planning | A | R | C | C | C | I | Responsible | Project Kick-off & Planning | Project Manager | Delivery Manager | Client PM, PMO | Business Stakeholders, Architects
Scope Finalization | A | R | C | C | C | I | Accountable | Scope Finalization | Business Analyst | Delivery Manager | Product Owner, Solution Lead | Development, QA Teams
Sprint Planning | A | R | R | R | C | I | Consulted | Resource Onboarding & Allocation | Team Leads / HR | Delivery Manager | PM, HR Business Partner | Client, PMO
Delivery Execution | A | R | R | R | I | I | Informed | Sprint Planning / Work Allocation | Scrum Master / PM | Delivery Manager | Technical Lead, QA Lead | Product Owner, Stakeholders
Change Request Management | A | R | C | C | C | I |  | Change Request Management | PM / BA | Delivery Manager | Client, Architecture Lead | Dev, QA
Risk & Issue Escalation | A | R | C | C | C | I |  | Risk & Issue Review / Escalation | PM / Team Leads | Delivery Manager | Client, Stakeholders | Governance Board, PMO
UAT Coordination | A | R | C | R | R | I |  | Status Reporting & Dashboards | PMO / Reporting Analyst | Delivery Manager | PM, Functional Leads | CXOs, Client PM
Go-Live Readiness | A | R | C | C | C | I |  | UAT Planning & Coordination | QA Lead / Client SME | Delivery Manager / Client | Business Analysts, Developers | All Delivery Stakeholders
Final Delivery Sign-Off | A | R | C | C | A | I |  | Go-Live Readiness / Cutover Planning | DevOps Lead, Infra Lead | Delivery Manager | Support Teams, QA | Client, IT Ops, PMO
[8 empty] | Post Go-Live Support & Hypercare | Support / Dev Team | Delivery Manager | Client IT / Ops | Client PMO, PM, Business Teams

## Health Metrics
Metric | Definition | Purpose | Measurement | Fixed-Price Application | T&M Application
Schedule Variance (SV) | Measures the difference between planned and actual progress against the project timeline. | To assess if the project is on schedule or delayed. | SV = Earned Value (EV) - Planned Value (PV). Positive SV indicates ahead of schedule; negative indicates delay. | Critical to ensure milestones (e.g., design, development) are met within the fixed timeline. Delays may require scope reduction or change requests. | Monitors progress per sprint/phase. Delays may increase hours billed, requiring client approval for extended timelines.
Cost Variance (CV) | Measures the difference between planned and actual costs. | To determine if the project is within budget. | CV = Earned Value (EV) - Actual Cost (AC). Positive CV indicates under budget; negative indicates overrun. | Essential to ensure costs stay within the fixed budget. Overruns impact vendor profitability unless scope changes are approved. | Tracks costs against estimated hours/rates. Overruns increase client costs, requiring oversight to control billing.
Earned Value (EV) | Quantifies the value of work completed compared to the planned budget. | To measure project progress in monetary terms. | EV = % of work completed × Total Budget. Compared to Planned Value (PV) and Actual Cost (AC). | Tracks if deliverables (e.g., website pages) are completed as planned within the fixed budget. | Monitors value delivered per sprint. Helps assess if billed hours align with progress.
Schedule Performance Index (SPI) | A ratio of earned value to planned value, indicating schedule efficiency. | To evaluate how efficiently the project is progressing against the timeline. | SPI = EV / PV. SPI > 1 indicates ahead of schedule; SPI < 1 indicates delay. | Ensures milestones are met on time to avoid penalties or scope adjustments in fixed contracts. | Tracks sprint progress. SPI < 1 may prompt discussions to adjust scope or extend timelines.
Cost Performance Index (CPI) | A ratio of earned value to actual cost, indicating cost efficiency. | To assess whether the project is within budget relative to work completed. | CPI = EV / AC. CPI > 1 indicates under budget; CPI < 1 indicates overrun. | Monitors if the vendor is spending efficiently to maintain profitability within the fixed price. | Tracks cost efficiency per sprint. CPI < 1 signals potential cost overruns, requiring client review.
Scope Creep Index | Measures changes to the project scope beyond the original agreement. | To track and control unauthorized scope expansions. | % of additional tasks/features not in the original SOW. Can be qualitative (e.g., number of change requests). | Critical to prevent scope creep, as additional work requires formal change requests to adjust cost/timeline. | Allows flexibility for scope changes, but tracks additions to ensure they align with client priorities and budget.
Quality Metrics | Measures the quality of deliverables against predefined standards. | To ensure deliverables meet requirements and client expectations. | - Defect rate (e.g., bugs per module) - Test case pass rate - Client acceptance rate | Ensures deliverables (e.g., software functionality) meet quality standards within the fixed scope to avoid rework costs. | Monitors quality per sprint. Defects may increase hours billed for fixes, requiring client oversight.
Risk Exposure | Quantifies the likelihood and impact of identified risks. | To identify and mitigate risks that could derail the project. | Risk Score = Probability × Impact. Monitored via a risk register. | Tracks risks (e.g., technical issues) that could increase costs, impacting vendor margins in fixed contracts. | Tracks risks (e.g., scope changes) that could increase hours/costs, requiring client approval for additional work.
Stakeholder Satisfaction | Gauges the satisfaction level of clients, team members, and other stakeholders. | To ensure alignment with expectations and maintain project support. | Surveys, feedback scores (e.g., 1–5 scale), or Net Promoter Score (NPS). | Ensures client satisfaction with fixed deliverables to secure final payment and avoid disputes. | Tracks ongoing client feedback per sprint to adjust priorities and maintain collaboration.
Resource Utilization Rate | Measures how effectively team resources are being used. | To optimize team productivity and allocation. | Utilization Rate = (Actual Hours Worked / Available Hours) × 100. | Ensures resources are used efficiently to complete work within the fixed budget and timeline. | Monitors hours billed to ensure team efficiency and alignment with client budget expectations.
Milestone Completion Rate | Tracks the percentage of milestones or deliverables completed on time. | To monitor progress against key project checkpoints. | % of milestones completed on schedule. | Critical to track milestone progress (e.g., design phase) to ensure the project stays on track within the fixed timeline. | Tracks sprint or phase completion to ensure iterative progress aligns with client goals.
Change Request Volume | Measures the number and impact of scope change requests. | To assess the stability of the project scope and manage changes. | Number of change requests and their impact on cost/timeline. | High change request volume indicates scope creep, requiring formal approval to adjust fixed cost/timeline. | Changes are more easily accommodated, but volume is tracked to manage costs and priorities.

## Key DM Techniques
Key Delivery Management Techniques
Technique | Definition | Purpose | Key Components | Fixed-Price Application | T&M Application | Example
Work Breakdown Structure (WBS) | A hierarchical decomposition of the project into tasks, subtasks, and deliverables. | To break down complex projects into manageable components for planning and tracking. | - Task list - Effort estimates - Dependencies - Deliverables | Ensures precise task definition to lock in scope and cost, critical for fixed budgets. | Defines flexible tasks or sprint goals, allowing iterative adjustments. | Fixed: WBS for a website: “Design: 50 hours, Development: 100 hours.” T&M: “Sprint 1: Design, 40–60 hours.”
Gantt Chart | A visual timeline showing tasks, durations, and dependencies. | To plan and track project schedules, ensuring timely delivery. | - Task bars - Milestones - Dependencies - Timeline | Maps fixed milestones to ensure adherence to the agreed timeline. | Tracks sprint progress with flexible timelines for iterative delivery. | Fixed: Gantt shows website launch by Week 12. T&M: Shows monthly sprints for an AI app.
Earned Value Management (EVM) | A method to measure project performance by comparing planned value (PV), earned value (EV), and actual cost (AC). | To track cost and schedule performance, identifying variances early. | - Schedule Variance (SV = EV - PV) - Cost Variance (CV = EV - AC) - SPI (EV/PV) - CPI (EV/AC) | Monitors if project stays within fixed budget and timeline, avoiding cost overruns. | Tracks value delivered per sprint to ensure billed hours align with progress. | Fixed: CV = -$2,000 indicates website project overrun. T&M: SPI = 0.8 signals sprint delay.
Risk Management | Identifying, assessing, and mitigating risks using tools like a RAID Log. | To proactively address uncertainties that could impact delivery. | - Risk identification - Probability/Impact - Mitigation plans - RAID Log | Mitigates risks (e.g., scope creep) to protect fixed budget, using cost buffers. | Tracks risks (e.g., requirement changes) to manage hours and client expectations. | Fixed: Buffer $5,000 for API risks. T&M: Bill extra hours for requirement changes.
Agile/Scrum Methodology | An iterative approach with sprints, daily stand-ups, and client feedback. | To deliver incrementally, adapting to changing requirements. | - Sprints (1–4 weeks) - Daily stand-ups - Product backlog - Sprint reviews | Less common but used for fixed-price agile projects with locked scope per sprint. | Ideal for T&M, enabling iterative development and flexible billing. | Fixed: Agile website project with fixed $20,000 per phase. T&M: AI chatbot with $120/hour sprints.
Waterfall Methodology | A linear approach with sequential phases (e.g., planning, execution, testing). | To deliver projects with well-defined, stable requirements. | - Phases (e.g., Design, Build) - Milestones - Deliverables | Preferred for Fixed-Price, as stable scope aligns with sequential delivery. | Less common for T&M due to limited flexibility, but used for phased billing. | Fixed: Website built in phases with fixed $25,000. T&M: Rare, but phased CRM development.
Change Management | A process to handle scope changes, including change requests and approvals. | To control scope creep and ensure alignment with client expectations. | - Change request process - Impact assessment - Approval workflow | Critical to manage scope changes, requiring formal requests to adjust cost/timeline. | Flexible, allowing scope changes to be billed as additional hours. | Fixed: Change request adds $5,000 for new feature. T&M: New feature adds 20 hours at $100/hour.
Stakeholder Communication Plan | A plan outlining how and when to communicate with stakeholders. | To ensure transparency, manage expectations, and gather feedback. | - Stakeholder list - Communication channels - Frequency (e.g., weekly reports) - Feedback mechanisms | Ensures client approval of fixed deliverables, minimizing disputes. | Facilitates ongoing client collaboration for sprint reviews and priority adjustments. | Fixed: Weekly status reports for website milestones. T&M: Biweekly sprint reviews for AI project.
Quality Assurance (QA) | Processes to ensure deliverables meet predefined standards (e.g., testing, reviews). | To deliver high-quality outputs, reducing rework and client dissatisfaction. | - Test plans - Defect tracking - Acceptance criteria - QA metrics (e.g., defect rate) | Ensures quality within fixed budget, avoiding vendor-funded rework. | Monitors quality per sprint, with fixes billed as additional hours. | Fixed: 5% defect rate in app testing. T&M: Bugs fixed in 10 extra hours.
Resource Management | Allocating and optimizing team resources (e.g., developers, testers). | To maximize productivity and control costs. | - Resource allocation plan - Utilization rate - Skill matrix | Optimizes resources to stay within fixed budget, avoiding overruns. | Tracks hours to ensure efficient billing and alignment with client budget. | Fixed: 80% utilization for website team. T&M: 90% utilization for AI developers.

## RAID Log & Planning
Components of a RAID Log |  |  |  | RAIG Log in FB Vs T&M |  |  |  | RAIG Log Template
Component | Definition | Purpose | Key Fields | Aspect | Fixed-Price Application | T&M Application | Example | ID | Category | Description | Probability | Impact | Risk Score | Owner | Status | Action Plan | Due Date
Risks | Potential uncertainties that could affect project outcomes (e.g., cost overruns, delays). | To identify, assess, and mitigate risks before they become issues. | - Risk ID - Description - Probability (e.g., Low/Medium/High) - Impact (e.g., Cost/Timeline) - Mitigation Plan - Owner - Status | Risks | Critical to identify risks (e.g., scope creep, technical issues) that could increase costs, as the vendor bears overrun risks. High risks may require cost buffers or push toward T&M. | Tracks risks (e.g., evolving requirements) that increase hours billed, requiring client oversight to manage costs. | Fixed: Risk of delayed client approval (Probability: 30%, Impact: $5,000). Mitigation: Add buffer to timeline. T&M: Risk of unclear requirements. Mitigation: Plan iterative reviews. | R1 | Risk | Unclear requirements | 40% | $5,000 | 2000 | PM | Open | Send questionnaire | 07/25/2025
Assumptions | Statements taken as true for planning but not yet validated (e.g., resource availability). | To document planning assumptions and validate them to avoid surprises. | - Assumption ID - Description - Impact if Invalid - Validation Plan - Owner - Status | Assumptions | Must be validated early to lock in scope and cost (e.g., “client provides content by Week 2”). Invalid assumptions trigger change requests. | Assumptions are flexible, validated iteratively (e.g., “features finalized per sprint”). Invalid assumptions adjust hours. | Fixed: Assumption: “API documentation provided.” Impact: $10,000 rework if invalid. T&M: Assumption: “Client prioritizes features monthly.” Impact: Additional sprint hours. | A1 | Assumption | Client provides content | - | 2-week delay | - | Client | Pending | Confirm delivery | 07/22/2025
Issues | Current problems affecting the project (e.g., missed milestone, defective deliverable). | To track and resolve issues to minimize their impact on delivery. | - Issue ID - Description - Impact - Resolution Plan - Owner - Status | Issues | Issues (e.g., defective deliverable) require swift resolution within the fixed budget, often at vendor expense. | Issues increase billed hours, requiring client approval for additional work. | Fixed: Issue: Bug in website module. Resolution: Vendor fixes within budget. T&M: Issue: Integration failure. Resolution: Bill 20 extra hours. | I1 | Issue | Bug in module | - | 10 hours | - | Developer | In Progress | Fix by testing | 07/23/2025
Dependencies | Tasks or deliverables reliant on external or internal factors (e.g., third-party API delivery). | To manage dependencies to prevent delays or bottlenecks. | - Dependency ID - Description - Dependent Task - Source (e.g., Client/Vendor) - Due Date - Owner - Status | Dependencies | Dependencies (e.g., client deliverables) are critical to meet fixed milestones. Delays may require change requests. | Dependencies are managed flexibly, with delays absorbed into sprints and billed accordingly. | Fixed: Dependency: Client provides content by Week 4. Delay impacts milestone. T&M: Dependency: Client feedback per sprint. Delay extends sprint hours. | D1 | Dependency | Client design approval | - | Milestone delay | - | Client | Open | Schedule review | 07/24/2025

## People Management Skills
People Management Techniques
Technique | Definition | Purpose | Key Components | Fixed-Price Application | T&M Application | Example
Resource Allocation and Planning | Assigning team members to tasks based on skills, availability, and project needs. | To optimize team productivity and ensure tasks are completed within budget and timeline. | - Skill matrix - Resource capacity plan - Task assignments - Utilization rate | Allocates resources to meet fixed milestones, ensuring efficiency within budget constraints. | Allocates resources flexibly per sprint, adjusting based on evolving scope. | Fixed: Assign 2 developers for 100 hours to website development. T&M: Assign 3 developers for 50–70 hours per AI sprint.
Team Communication and Collaboration | Establishing clear communication channels and fostering teamwork. | To ensure alignment, reduce misunderstandings, and enhance team cohesion. | - Communication plan - Regular meetings (e.g., stand-ups) - Collaboration tools (e.g., Slack, Teams) - Feedback loops | Ensures team alignment with fixed scope and milestones, minimizing rework. | Facilitates ongoing collaboration for iterative sprints and client feedback. | Fixed: Weekly team meetings to track website milestone progress. T&M: Daily stand-ups for AI sprint planning.
Performance Management | Monitoring and evaluating team member performance against project goals. | To maintain high productivity and address performance gaps. | - KPIs (e.g., task completion rate) - Performance reviews - Feedback sessions - Recognition programs | Tracks performance to ensure tasks are completed within fixed budget and timeline. | Monitors performance per sprint, adjusting roles or hours as needed. | Fixed: Developer completes 95% of tasks on time. T&M: Developer’s sprint output reviewed, with feedback to improve next sprint.
Conflict Resolution | Addressing interpersonal or role-based conflicts within the team or with stakeholders. | To maintain team morale and prevent delays. | - Conflict identification - Mediation process - Resolution strategies - Escalation path | Resolves conflicts quickly to avoid delays in fixed milestones, as delays impact vendor costs. | Manages conflicts to ensure smooth sprint execution, with client involvement if needed. | Fixed: Resolve developer-client disagreement on design within 2 days. T&M: Mediate team dispute on sprint priorities.
Motivation and Engagement | Encouraging team members through recognition, incentives, and clear goals. | To boost morale, productivity, and retention, ensuring consistent delivery. | - Recognition programs - Incentives (e.g., bonuses) - Clear role definitions - Team-building activities | Motivates team to meet fixed deadlines and quality standards within budget. | Encourages team to deliver value in iterative sprints, maintaining client satisfaction. | Fixed: Bonus for early website delivery. T&M: Recognition for high-quality AI sprint output.
Training and Skill Development | Providing training to enhance team skills relevant to project needs. | To ensure the team has the capabilities to deliver high-quality work. | - Skill gap analysis - Training plans - On-the-job mentoring - Certification programs | Ensures team is skilled to deliver fixed scope without rework, saving costs. | Upskills team for evolving T&M requirements, billed as part of hours. | Fixed: Train developer on CMS for website project. T&M: Train team on new AI framework mid-project.
Stakeholder Management | Engaging and managing client and other stakeholders’ expectations. | To align project delivery with client needs and ensure satisfaction. | - Stakeholder map - Expectation setting - Regular updates - Feedback sessions | Ensures client approves fixed deliverables, avoiding disputes over scope. | Facilitates ongoing client collaboration for sprint reviews and scope adjustments. | Fixed: Client approves website design milestone. T&M: Client prioritizes AI features in sprint review.
Capacity Management | Balancing team workload to prevent burnout and ensure sustainable delivery. | To maintain team health and consistent productivity. | - Workload analysis - Overtime monitoring - Resource leveling - Burnout indicators | Balances workload to meet fixed deadlines without compromising quality. | Adjusts workload per sprint to align with T&M hours and client budget. | Fixed: Limit developer hours to 40/week for website. T&M: Adjust hours to 50/week for AI sprint rush.

## DM_Agile,Scrum,Waterfall
Agile, Scrum, and Waterfall in Delivery Management
Aspect | Agile | Scrum | Waterfall
Definition | Iterative, flexible methodology prioritizing collaboration and adaptability. | Agile framework with time-boxed sprints, defined roles, and iterative delivery. | Linear, sequential methodology with distinct phases and fixed requirements.
Core Principles | - Individuals over processes - Working software over documentation - Customer collaboration - Responding to change | - Transparency - Inspection - Adaptation - Iterative delivery | - Upfront planning - Sequential phases - Fixed scope - Comprehensive documentation
Key Processes | - Iterative development - Customer collaboration - Continuous planning - Daily coordination - Retrospectives | - Sprint planning - Daily Scrum - Sprint execution - Sprint review - Sprint retrospective | - Requirements gathering - Design - Development - Testing - Deployment - Maintenance
Key Artifacts | - Product backlog - Iteration backlog - Working increments | - Product backlog - Sprint backlog - Increment - Definition of Done | - BRD/FRS - Design specs - Test plans - Final deliverables
Roles | - Product Owner - Team - Agile Coach (optional) | - Product Owner - Scrum Master - Development Team | - Project Manager - Analysts - Developers - Testers - Stakeholders
Tools | - Jira - Trello - Confluence - Slack | - Jira - Azure DevOps - Scrum boards - Burndown charts | - MS Project - Excel - Gantt charts - RAID Log
Fixed-Price Application | - Define sprint deliverables to lock scope per iteration - Use milestones for payments - Control scope creep via change requests | - Pre-agree sprint scope and cost (e.g., $10,000/sprint) - Align reviews with milestones | - Ideal for stable scope - Align phases with fixed milestones - Use WBS and Gantt for cost/timeline control
T&M Application | - Flexible scope adjustments per iteration - Bill hours based on effort (e.g., $120/hour) | - Bill hours per sprint - Adjust backlog based on client feedback | - Less common; bill per phase with some flexibility - Track hours for deliverables
Delivery Management Benefits | - Adapts to changes - Early value delivery - High client involvement | - Predictable sprint cycles - Transparent progress - Team empowerment | - Clear planning - Predictable outcomes - Suited for stable scope
Challenges | - Scope creep risk in Fixed-Price - Needs active client engagement | - Requires disciplined backlog management - Client commitment for reviews | - Inflexible to changes - Risky for unclear requirements
Example | Fixed: Website with fixed $20,000, delivered in 3 sprints with defined features. T&M: AI app with evolving features, billed at $120/hour per iteration. | Fixed: CRM with $15,000/sprint, 4 sprints with locked scope. T&M: Chatbot with $100/hour, sprints adjusted per client feedback. | Fixed: Website with $25,000, delivered in 3 phases (Design, Build, Test). T&M: CRM with $10,000/phase, some scope flexibility.

## T-Shirt Sizing Matrix
T-Shirt Sizing Matrix
Aspect | Definition | Purpose | Key Components | Fixed-Price Application | T&M Application | Example
T-Shirt Sizing Matrix | A qualitative method using T-shirt sizes (XS, S, M, L, XL) to estimate task effort or complexity. | To provide high-level estimates for planning and contract type decisions. | - T-shirt sizes - Task/feature list - Sizing criteria - Assumptions - Risks | Ensures scope clarity for accurate fixed-cost estimation, with buffers for large tasks. | Supports flexible planning for iterative delivery, aligning hours with task size. | Fixed: Website login page = S, API integration = M. T&M: AI feature = L, adjustable per sprint.
Sizing Criteria | Factors used to assign sizes (e.g., complexity, dependencies, unknowns). | To standardize estimation across tasks. | - Complexity level - Technical skills - Dependencies - Risk level | Defines criteria to lock scope (e.g., S = 1–3 days, low complexity). | Allows flexible criteria (e.g., L = 2–4 weeks, high unknowns). | Fixed: S = Simple UI, M = API with docs. T&M: L = AI with evolving specs.
Collaborative Estimation | Team and stakeholder workshops to assign sizes. | To align on effort and reduce estimation errors. | - Planning poker - Team discussions - Stakeholder input | Ensures team consensus on fixed scope to avoid cost overruns. | Facilitates iterative sizing with client input per sprint. | Fixed: Team agrees login page = S. T&M: Client prioritizes AI feature = L.
Matrix Documentation | A table capturing tasks, sizes, and assumptions. | To centralize estimates for planning and tracking. | - Task/feature - T-shirt size - Assumptions - Risks - Notes | Documents stable scope for fixed budget (e.g., $25,000 for S/M tasks). | Tracks flexible scope for billing (e.g., L tasks = 50–70 hours). | Fixed: Matrix lists website tasks with sizes. T&M: Matrix tracks AI sprint tasks.
Contract Type Decision | Using sizes to assess scope stability for Fixed or T&M. | To choose the appropriate contract based on scope clarity. | - Size distribution - Risk assessment - Scope stability | Stable sizes (XS, S, M) support Fixed-Price with clear scope. | Variable sizes (L, XL) favor T&M for flexibility. | Fixed: Mostly S/M tasks for website = Fixed-Price. T&M: L/XL AI tasks = T&M.
Resource Planning | Allocating resources based on task sizes. | To optimize team assignments for efficiency. | - Resource needs per size - Skill requirements - Utilization rate | Allocates resources to meet fixed milestones within budget. | Adjusts resources per sprint based on size and client needs. | Fixed: 2 developers for M-sized website tasks. T&M: 3 developers for L-sized AI tasks.
Risk Integration | Linking large sizes (L, XL) to RAID Log risks. | To mitigate uncertainties impacting delivery. | - Risk identification - Mitigation plans - RAID Log | Adds buffers for L/XL tasks to protect fixed budget. | Tracks L/XL tasks as risks, billing extra hours for mitigation. | Fixed: L-sized API task = $5,000 buffer. T&M: XL AI task = 20 extra hours.

## DM_Other Matrices
Matrix | Definition | Purpose | Key Components | Fixed-Price Application | T&M Application | Example
RACI Matrix | Defines roles as Responsible, Accountable, Consulted, Informed for tasks/deliverables. | Clarifies task ownership to avoid confusion and ensure accountability. | - Tasks/deliverables - Roles (R, A, C, I) - Team members/stakeholders | Ensures clear roles to meet fixed milestones, avoiding delays that impact budget. | Supports flexible role assignments per sprint, adapting to evolving scope. | Fixed: Developer (R) for website coding, PM (A) for milestone approval. T&M: Client (C) in AI sprint reviews.
Risk Assessment Matrix | Evaluates risks by probability and impact on a grid (e.g., 3x3). | Prioritizes risks for mitigation to protect project outcomes. | - Risks - Probability (Low/Medium/High) - Impact (Cost/Timeline/Quality) - Mitigation plans | Adds buffers for high-impact risks to protect fixed budget. Integrates with RAID Log. | Tracks risks that increase hours, ensuring client approval for extra work. | Fixed: API delay (High Probability, $5,000 Impact). T&M: Requirement change (Medium Probability, 20 extra hours).
Priority Matrix (Impact-Effort) | Prioritizes tasks by impact (value) and effort (resources/time) on a 2x2 grid. | Focuses on high-impact, low-effort tasks to maximize value. | - Tasks/features - Impact (High/Low) - Effort (High/Low) - Priority quadrants | Prioritizes tasks within fixed scope to optimize budget use. | Guides sprint planning to focus on high-value features, billing based on effort. | Fixed: High-impact login page (Low Effort) prioritized. T&M: High-impact AI feature (High Effort) planned for next sprint.
MoSCoW Prioritization Matrix | Categorizes tasks as Must Have, Should Have, Could Have, Won’t Have. | Manages scope to deliver critical requirements within constraints. | - Requirements list - Categories (M, S, C, W) - Stakeholder input | Locks Must-Have requirements for fixed scope, minimizing scope creep. | Prioritizes Must-Have features per sprint, adjusting Should/Could items. | Fixed: Website login = Must, Blog = Could. T&M: AI core = Must, Multilingual = Could.
Stakeholder Analysis Matrix | Maps stakeholders by power and interest on a 2x2 grid. | Tailors communication to manage expectations and engagement. | - Stakeholders - Power (High/Low) - Interest (High/Low) - Engagement strategy | Ensures key stakeholders approve fixed deliverables, avoiding disputes. | Engages stakeholders in sprint reviews to align on evolving scope. | Fixed: Client (High Power, High Interest) gets weekly updates. T&M: Client (High Interest) joins sprint reviews.
Story Point Estimation Matrix | Assigns numerical story points (e.g., Fibonacci: 1, 2, 3, 5, 8) to tasks in Agile. | Refines effort estimates for sprint planning and resource allocation. | - User stories - Story points - Planning poker - Complexity/risk factors | Refines T-Shirt sizes for fixed sprints, ensuring cost certainty. | Estimates effort per sprint, aligning hours with client budget. | Fixed: Login page = 3 points, API = 8 points. T&M: AI feature = 13 points, adjustable per sprint.

## Team Velocity_Agile
Aspect | Definition | Purpose | Key Components | Fixed-Price Application | T&M Application | Example
Team Velocity | Average work (story points, hours, or tasks) completed per sprint. | To plan sprints, forecast timelines, and manage delivery expectations. | - Story points - Completed user stories - Average over sprints - Definition of Done | Ensures predictable sprint delivery within fixed budget and timeline. | Guides sprint planning and billing for iterative delivery with evolving scope. | Fixed: 15 points/sprint for website, predicts 4 sprints for 60-point backlog. T&M: 20 points/sprint for AI, adjusts hours billed.
Calculation | Sum of completed story points per sprint, averaged over 3–5 sprints. | To provide a reliable estimate of team capacity. | - Story point summation - Sprint data - Adjustment factors | Uses stable velocity to lock sprint scope, ensuring cost certainty. | Uses velocity to estimate hours per sprint, aligning with client budget. | Fixed: Average 15 points over 3 sprints for website. T&M: 18 points/sprint for AI, billing 90 hours at $120/hour.
Sprint Planning | Selecting backlog items based on velocity. | To set achievable sprint goals. | - Product backlog - Sprint backlog - Velocity data | Plans fixed sprints with defined points to meet milestones. | Plans flexible sprints, adjusting points based on client priorities. | Fixed: Plan 15-point sprint for website login. T&M: Plan 20-point sprint for AI feature, adjustable.
Forecasting | Estimating project timeline using velocity and backlog size. | To predict delivery dates for stakeholders. | - Total backlog points - Average velocity - Timeline estimate | Forecasts fixed timeline (e.g., 4 sprints for 60 points). | Estimates flexible timeline, updating based on scope changes. | Fixed: 60-point website backlog ÷ 15 points/sprint = 4 sprints. T&M: 80-point AI backlog ÷ 20 points/sprint = ~4 sprints, adjustable.
Contract Type Decision | Using velocity to assess scope stability for Fixed or T&M. | To choose appropriate contract based on predictability. | - Velocity stability - Backlog clarity - Risk assessment | Stable velocity supports Fixed-Price with predictable sprints. | Variable velocity favors T&M for flexibility in hours and scope. | Fixed: Stable 15 points/sprint supports $25,000 website bid. T&M: Variable 15–20 points/sprint suits AI at $120/hour.
Risk Integration | Linking velocity fluctuations to RAID Log risks. | To mitigate factors affecting team performance. | - Velocity trends - Risks (e.g., dependencies) - Mitigation plans | Addresses velocity drops (e.g., delays) with buffers to protect budget. | Tracks velocity changes, billing extra hours for mitigation. | Fixed: Low velocity (10 points) due to API delay, add $5,000 buffer. T&M: Low velocity, bill 10 extra hours for AI.
Performance Improvement | Analyzing velocity trends to optimize team output. | To address bottlenecks and enhance productivity. | - Velocity charts - Retrospectives - Process improvements | Ensures team meets fixed milestones by addressing low velocity. | Improves sprint output, ensuring value for billed hours. | Fixed: Low velocity prompts training for website team. T&M: Retrospective improves AI sprint velocity.

## DM_Other Key Components_Agile
Consideration | Definition | Purpose | Key Components | Fixed-Price Application | T&M Application | Example
Team Capacity | Total available work hours/effort, accounting for availability and skills. | Ensures realistic task allocation to avoid burnout or delays. | - Resource availability - Skill matrix - Utilization rate - Non-project time | Allocates resources to meet fixed milestones within budget, optimizing efficiency. | Adjusts resources per sprint, billing hours based on capacity. | Fixed: 2 developers at 80 hours each for website project. T&M: 3 developers at 50–70 hours/sprint for AI project.
Burndown Rate | Tracks remaining work in a sprint/project via a burndown chart. | Monitors progress to ensure timely delivery and identify delays. | - Burndown chart - Story points/hours - Sprint progress - Blockers | Tracks sprint progress to meet fixed milestones, avoiding cost overruns. | Monitors sprint progress, adjusting hours billed for delays. | Fixed: Website sprint burndown shows 10 points remaining, prompts action. T&M: AI sprint burndown adjusts hours for blockers.
Definition of Done (DoD) | Criteria for a deliverable to be considered complete. | Ensures consistent quality, reducing rework and disputes. | - Quality standards - Testing requirements - Client approval - Documentation | Ensures deliverables meet fixed scope, avoiding vendor-funded rework. | Defines quality per sprint, billing extra hours for fixes. | Fixed: Website login page coded, tested, and client-approved. T&M: AI feature tested and demoed in sprint review.
Cycle Time | Time to complete a task/user story from start to finish. | Measures process efficiency and identifies bottlenecks. | - Task start/end dates - Workflow stages - Bottleneck analysis | Tracks efficiency to meet fixed timelines, avoiding delays. | Optimizes sprint workflows, ensuring value for billed hours. | Fixed: Website login page cycle time = 3 days. T&M: AI feature cycle time = 10 days, adjusted for complexity.
Stakeholder Engagement | Level of stakeholder involvement and communication. | Aligns deliverables with expectations, ensuring satisfaction. | - Stakeholder map - Communication plan - Feedback loops - Engagement metrics | Ensures client approvals for fixed deliverables, minimizing disputes. | Facilitates iterative feedback in sprints, adjusting scope. | Fixed: Client approves website milestones weekly. T&M: Client joins AI sprint reviews to prioritize features.
Technical Debt | Accumulated cost of shortcuts requiring future rework. | Balances speed vs. quality to minimize long-term risks. | - Debt log - Rework estimates - Prioritization - Mitigation plans | Manages debt to avoid rework within fixed budget. | Tracks debt, billing hours for future fixes. | Fixed: Website quick fix adds 5 hours debt, mitigated in budget. T&M: AI shortcut adds 10 hours debt, billed later.